## SharePoint Deployment Plan
TPCS SharePoint Deployment Plan
Project Name | SharePoint Deployment Plan for 100 Users
Project Manager | [6 empty] | Project Legend
Solutions Architect-DB
SharePoint Architect
Project Consultant | [6 empty] | Not Started
Start Date | [6 empty] | Inprogress
End Date | [6 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
Understand the Customer Requirement
Design The Logical Architecture- HLD
Create an UAT Plan
Create a Project Plan (WBS)
Create a Low Level design (LLD)- Technical Execution Document
Build Phase | Repare Servers for Shairpoint
Update Servres
Install Symantec Antivirus
Create Active Dairtory Server
Configer Active Dairtory
Create Login Acount
Test All a above
SharePoint Deployment Phase | Install SQL Server
Assigne Promation to user
Install Shairpoint Prerequisite
Install Shairpoint
Test All a above
Crete Frist site
Test Site
Stablization and HandoverPhase | Training the IT team how to Handle services in Azure
Handover the Documents
Handover the Credential

## XYZ Database Migration Project
TPCS Database Migration to Azure
Project Name | Migrate and Transit the Database from on-prem to Azure Cloud
Project Manager | [6 empty] | Project Legend
Solutions Architect-DB
Azure Architect
Project Consultant | [6 empty] | Not Started
Start Date | [6 empty] | Inprogress
End Date | [6 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
Understand the Customer Requirement
Design The Logical Architecture- HLD
Create an UAT Plan
Create a Project Plan (WBS)
Create a Low Level design (LLD)- Technical Execution Document
Build Phase
Create a Azure Account for TPCS
Set the Region
Define the Login Account
Create IAM Roles
Check the permission using policy simulator
Create a Resource Group
Migration & Transition Phase | Enable Strech Database Features on-Prem
Strech the Database Table "Incident" to Azure
Configure SQL database while creating
Perform the UAT of the Streth Database
Install SQL Migration Tool
Perform the Accessesment on the Table
Perform the Migration
UAT Phase | Perform the Query on SQL on Azure for Stretch Database
Connect the SQL from Azure to On-Prem
Perform the general Task
Stablization and HandoverPhase | Training the IT team how to Handle services in Azure
Handover the Documents
Handover the Credential

## Xyz Project
xyx WordPress App Deployment on AWS
Project Name | WordPress with RDS Deployment on Amazon AWS
Project Manager | [6 empty] | Project Legend
Project Consultant | [6 empty] | Not Started
Start Date | [6 empty] | Inprogress
End Date | [6 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
Understand the Customer Requirement
Design The Logical Architecture- HLD
Create an UAT Plan
Create a Project Plan (WBS)
Create a Low Level design (LLD)- Technical Execution Document
Build Phase
Create a AWS Account for xyx
Set the Region
Define the Login Account
Create IAM Roles
Check the permission using policy simulator
Create a security group
Create a MySQL database for your WordPress site
• Configure connectivity and network configuration for RDS Instance
• Create an EC2 Instance
• Allow your EC2 instance to access your RDS database
• Create a database user for your WordPress application and give it permission to access
the “wordpress” database
• Installing the Apache web server on EC2
• download the WordPress software and set up the configuration on EC2
• Deploying WordPress
• Explore your new web site
UAT Phase | Access the Wordpress App from Outside
Login on Wordpress App
Perform the general Task
Stablization and HandoverPhase | Training the IT team how to Handle services in AWS
Handover the Documents
Handover the Credential

## Xyz Migration Project
TPCS Server Migration to AWS
Project Name | Migration of Server to AWS Cloud
Project Goal | TPCS Has Servers Running on Premises , TPCS wants to Migrate the Server to AWS Cloud . The Server Include App Server , File Server and MySQL Databse Server
Project Manager | [6 empty] | Project Legend
Project Consultant | [6 empty] | Not Started
Start Date | [6 empty] | Inprogress
End Date | [6 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
Understand the Customer Requirement
Design The Logical Architecture- HLD
Create an UAT Plan
Create a Project Plan (WBS)
Create a Low Level design (LLD)- Technical Execution Document
Build Phase
Create a AWS Account for TPCS
Set the Region
Define the Login Account
Create IAM Roles
Check the permission using policy simulator
Create a security group
Create a Centos Linux virtual machine
• Configure the host name,ip and the user account
• Install Apache web server
• Create a windows virtual machine
• Install the mysql database virtual machine
Create a file server
Migration Phase | Perform the Assessment using MAP Tool
Perform the Bandwidth Aseesment
Perform the Cost Estimate
Use AWS Migrate /Endure to Migrate the App Server
Setup the migration project in cloud endure
Create a custom policy and user in aws
Setup the source and target migration in aws endure
Install endure agent on onpremises server
Set the blueprint
Launch the cutover migration
Migarte the MYSQL data to S3 and From S3 Migaret to RDS
Migrate the File Server Data to EFS/S3
UAT Phase | Launch the App VM in AWS
Access the Mysql Database from Mysql tool
Access the EFS/S3 using browser /Mounting
Stablization and HandoverPhase | Training the IT team how to Handle services in AWS
Handover the Documents
Handover the Credential